## Sheet1 (hidden)
No: Teams | 56
Expected Output | 324
Expected Output/ Slot | 54
| 8.00-10.00 | 10.00-12.00 | 12.00-2.00 | 2.00-4.00 | 4.00-6.00 | 6.00-8.00 | Total
FRIDAY 5/1/2020 Planned | 54 | 54 | 54 | 54 | 54 | 54 | 324 |  | HFC | 50 | 300
|  | 54 | 54 | 54 | 54 | 54 | 270 |  | GPON | 6 | 24
|  |  | 54 | 54 | 54 | 54 | 216 |  |  |  | 324
|  |  |  | 54 | 54 | 54 | 162 |  |  |  | 54
[5 empty] | 54 | 54 | 108
[6 empty] | 54 | 54
FRIDAY 5/1/2020 Actual | 26 | 81 | 74 | 80 | 53 | 23 | 337
|  | 26 | 81 | 74 | 80 | 53 | 314
|  |  | 26 | 81 | 74 | 80 | 261
|  |  |  | 26 | 81 | 74 | 181
[5 empty] | 26 | 81 | 107
[6 empty] | 26 | 26
Deviation
| 8.00-10.00 | 10.00-12.00 | 12.00-2.00 | 2.00-4.00 | 4.00-6.00 | 6.00-8.00 | Total
Available Jobs/Slot | 395 | 307 | 201 | 172 | 149 | 140 |  | 1364
Undoable Job | 21 | 8 | 19 | 12 | 8 | 28
Actual Possible Output | 374 | 299 | 182 | 160 | 141 | 112 | 0
Jobs Done

## UNDOABLE AND TRUCK ROLLS
SLOT | CLIENT CODE | UPDATES
6AM-8AM
8AM-10AM | 002-026870 | MDU NOT READY
10AM-12PM
12PM-2PM
2PM-4PM
4PM-6PM
6PM-8PM
8PM-10PM

## Sheet2
DATE | TIME IN | TIME COMPLETED | ACCOUNT NAME | WORK ORDER | ACCOUNT NO. | JOB TYPE | STATUS | TEAM
2021-12-15 | 7:00 | 11:40 | WILSON MUGAMBI THIURU | 42130108 | 002-864791 | GPON SHIFT CONNECT | COMPLETED | DET 6
2021-12-15 | 7:00 | 11:43 | MARY KAMUYU | 42137404 | 002-039321 | HFC INTERNET INSTALL | COMPLETED | DET 2
2021-12-15 | 7:00 | 1:15 | CUSTODIO PAULINE DIAS | 42138358 | 002-006775 | DISCONNECT DROP CABLE | COMPLETED | DET 2
2021-12-15 | 7:00 | 3:44 | JOAN WANGUI | 42138252 | 002-038527 | GPON INSTALL | COMPLETED | DET 6
2021-12-15 | 7:00 | 4:10 | BETTY KAMAU | 42138997 | 002-108918 | SUPPORT | COMPLETED | DET 2 | RG6 CABLE WITH TWO JOINERS
2021-12-15 | 7:00 | 5:21 | NGONG MATONYOK WHOLESALERS | 42139595 | 002-039367 | HFC INTERNET INSTALL | COMPLETED | DET 2
2021-12-15 | 7:00 | 6:03 | JUDY OLUOCH | 42140558 | 002-039376 | HFC TRIPPLE PLAY | COMPLETED | DET 6
2021-12-15 | 7:00 | 6:18 | WILSON MUGAMBI THIURU | 42130108 | 002-864791 | DISCONNECT DROP CABLE | COMPLETED | DET 6
2021-12-15 | 7:00 | 6:53 | GATHONI KUNGU | 42140921 | 002-162402 | EQUIPMENT PICKUP | COMPLETED | DET 2
6
1

## 16DECEMBER 2021
TARGET PER DAY | 7
NUMBER OF TEAMS | 2
TOTAL EXPECTED OUTPUT PER SLOT | 14
| 6.00-8.00 | 8.00-10.00 | 10.00-12.00 | 12.00-2.00 | 2.00-4.00 | 4.00-6.00 | 6.00-8.00 | 8:00-9:00 | TOTAL
DET 2 |  |  | 1 | 1 |  | 2 | 1 |  | 5 | 10
DET 6 |  |  | 1 |  | 1 |  | 2 |  | 4
TOTAL DONE
Customer Rescheduling/to call back
Customer Unreachable
G-TECH Technical (Routing)
Addtap
Client/ Management access issue/ wrongly addressed
WGK Technical (Signals/Approval)
Commercial (Coverage,MDU,NSR)
PreWired(No power)
Total Undoable Jobs per Slot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28– 7– 2020
[5 empty] | 4" | ?;LKJHGFDSDFGHJMK,L.;/'