## Sheet1 (hidden)
No: Teams | 56
Expected Output | 324
Expected Output/ Slot | 54
| 8.00-10.00 | 10.00-12.00 | 12.00-2.00 | 2.00-4.00 | 4.00-6.00 | 6.00-8.00 | Total
FRIDAY 5/1/2020 Planned | 54 | 54 | 54 | 54 | 54 | 54 | 324 |  | HFC | 50 | 300
|  | 54 | 54 | 54 | 54 | 54 | 270 |  | GPON | 6 | 24
|  |  | 54 | 54 | 54 | 54 | 216 |  |  |  | 324
|  |  |  | 54 | 54 | 54 | 162 |  |  |  | 54
[5 empty] | 54 | 54 | 108
[6 empty] | 54 | 54
FRIDAY 5/1/2020 Actual | 26 | 81 | 74 | 80 | 53 | 23 | 337
|  | 26 | 81 | 74 | 80 | 53 | 314
|  |  | 26 | 81 | 74 | 80 | 261
|  |  |  | 26 | 81 | 74 | 181
[5 empty] | 26 | 81 | 107
[6 empty] | 26 | 26
Deviation
| 8.00-10.00 | 10.00-12.00 | 12.00-2.00 | 2.00-4.00 | 4.00-6.00 | 6.00-8.00 | Total
Available Jobs/Slot | 395 | 307 | 201 | 172 | 149 | 140 |  | 1364
Undoable Job | 21 | 8 | 19 | 12 | 8 | 28
Actual Possible Output | 374 | 299 | 182 | 160 | 141 | 112 | 0
Jobs Done

## UNDOABLE AND TRUCK ROLLS
SLOT | CLIENT CODE | UPDATES
6AM-8AM
8AM-10AM | 002-026870 | MDU NOT READY
10AM-12PM
12PM-2PM
2PM-4PM
4PM-6PM
6PM-8PM
8PM-10PM

## Sheet2
DATE | TIME IN | TIME COMPLETED | ACCOUNT NAME | WORK ORDER | ACCOUNT NO. | JOB TYPE | STATUS | TEAM
2021-11-01 | 9:30 | 12:15pm | TIMOTHY THEURI | 41968696 | 002-241017 | HFC EQUIPMENT UPGRADE | COMPLETED | DET 2
2021-11-01 | 10:00 | 15:42 | PK VET SUPPLIES LIMITED | 41964556 | 002-198275 | HFC SUPPORT | COMPLETED AT 03:42 | DET 6 | t client's premise,, the alternative number given not picking up calls 254712919814 UPDATED 10:35AM
2021-11-01 | 11:55 | 13:36 | DIANA OKUMU | 41907475 | 002-248429 | HFC SHIFT CONNECT | PENDING | DET 6 | COMPLEX SITE | Conduit blocked,, management to unblock and call us back
2021-11-01 | 10:31 | 1:24 | TONIDA AKINYI | 41973249 | 002-809377 | DISCONNECT DROP CABLE | COMPLETED | DET 2
2021-11-01 | 10:31 | 1:35 | TONIDA AKINYI | 41973249 | 002-809377 | HFC SHIFT CONNECT | COMPLETED | DET 2
2021-11-01 | 1:50 | 2:04 | DIANA OKUMU | 41907475 | 002-248429 | DISCONNECT DROP CABLE | COMPLETED | DET 6
2021-11-01 | 2:00 | 2:24 | CAMPDE VOICES | 41967619 | 002-944079 | HFC SUPPORT | NET OKAY | DET 2 | Client says his net is okay yesterday he called back and informed the office Incase of anything he will inform the office NB:we should not interrupt the router cos it's an office and they are working
2021-11-01 | 3:00 | 4:05 | RISPA ODHIAMBO | 41971142 | 002-070097 | HFC SHIFT CONNECT | COMPLETED | DET 2
2021-11-01 | 3:50 | 4:31 | ELIAS MESERET | 41979948 | 002-038381 | TRIPPLE PLAY + DLINK | COMPLETED | DET 6
2021-11-01 | 5:10 | 5:41 | BRYAN MUINDI | 41979756 | 002-148863 | DISCONNECT DROP CABLE | COMPLETED | DET 6
2021-11-01 | 5:30 | 6:06 | LOYCE NYAMANGE | 41979317 | 002-132543 | HFC SHIFT CONNECT | ESCALATED | DET 2 | MDU NOT READY
2021-11-01 | 5:50 | 6:26 | SALIMAH MADHANI | 41977379 | 002-054500 | HFC SUPPORT | COMPLETED | DET 6
2021-11-01 | 6:10 | 6:41 | DEREJE CHERINET | 41979329 | 002-037247 | HFC INTERNET INSTALL | COMPLETED | DET 2
2021-11-01 | 6:30 | 6:36 | SAMMY NGERA | 41976961 | 002-275921 | HFC SUPPORT | COMPLETED | DET 6 | SUSPECTED OUTAGE RESTORED
2021-11-01 | 7:00 | 8:49 | JOSEPH KARIUK | 41979948 | 002-229142 | HFC SUPPORT | COMPLETED | DET 6
2021-11-01 | 7:30 | 9:41 | ANGUILE DIDIER | 41977646 | 002-079754 | HFC SUPPORT | COMPLETED | DET 2
2021-11-01 | 8:50 | 9:51 | ALLY SHUNUU | 41979948 | 002-862325 | HFC SHIFT CONNECT | COMPLETED | DET 6
1

## 1ST DEC 2021 PERFORMANCE
TARGET PER DAY | 6
NUMBER OF TEAMS | 2
TOTAL EXPECTED OUTPUT PER SLOT | 12
| 6.00-8.00 | 8.00-10.00 | 10.00-12.00 | 12.00-2.00 | 2.00-4.00 | 4.00-6.00 | 6.00-8.00 | 8:00-9:00 | TOTAL | ESCALATIONS
DET 2 |  |  | 1 | 2 | 2 | 1 | 1 | 1 | 8 |  | 16
DET 6 |  |  |  |  | 2 | 1 | 2 | 1 | 9
TOTAL DONE
Customer Rescheduling/to call back
Customer Unreachable
G-TECH Technical (Routing)
Addtap
Client/ Management access issue/ wrongly addressed
WGK Technical (Signals/Approval)
Commercial (Coverage,MDU,NSR)
PreWired(No power)
Total Undoable Jobs per Slot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28– 7– 2020
[5 empty] | 4" | ?;LKJHGFDSDFGHJMK,L.;/'