## Sheet1 (hidden)
No: Teams | 56
Expected Output | 324
Expected Output/ Slot | 54
| 8.00-10.00 | 10.00-12.00 | 12.00-2.00 | 2.00-4.00 | 4.00-6.00 | 6.00-8.00 | Total
FRIDAY 5/1/2020 Planned | 54 | 54 | 54 | 54 | 54 | 54 | 324 |  | HFC | 50 | 300
|  | 54 | 54 | 54 | 54 | 54 | 270 |  | GPON | 6 | 24
|  |  | 54 | 54 | 54 | 54 | 216 |  |  |  | 324
|  |  |  | 54 | 54 | 54 | 162 |  |  |  | 54
[5 empty] | 54 | 54 | 108
[6 empty] | 54 | 54
FRIDAY 5/1/2020 Actual | 26 | 81 | 74 | 80 | 53 | 23 | 337
|  | 26 | 81 | 74 | 80 | 53 | 314
|  |  | 26 | 81 | 74 | 80 | 261
|  |  |  | 26 | 81 | 74 | 181
[5 empty] | 26 | 81 | 107
[6 empty] | 26 | 26
Deviation
| 8.00-10.00 | 10.00-12.00 | 12.00-2.00 | 2.00-4.00 | 4.00-6.00 | 6.00-8.00 | Total
Available Jobs/Slot | 395 | 307 | 201 | 172 | 149 | 140 |  | 1364
Undoable Job | 21 | 8 | 19 | 12 | 8 | 28
Actual Possible Output | 374 | 299 | 182 | 160 | 141 | 112 | 0
Jobs Done

## UNDOABLE AND TRUCK ROLLS
SLOT | CLIENT CODE | UPDATES
6AM-8AM
8AM-10AM | 002-026870 | MDU NOT READY
10AM-12PM
12PM-2PM
2PM-4PM
4PM-6PM
6PM-8PM
8PM-10PM

## Sheet2
DATE | TIME IN | TIME COMPLETED | ACCOUNT NAME | WORK ORDER | ACCOUNT NO. | JOB TYPE | STATUS | TEAM
2021-12-15 | 7:00 | 10:55 | DANIEL MADIT THON DUOP |  | 002-109249 | DLINK SUPPORT | COMPLETED | DET 2
2021-12-15 | 7:00 | 11:21 | ABEL BELATHEW |  | 002-207003 | HFC SHIFTING INSTALL | COMPLETED | DET 2
2021-12-15 | 7:00 | 11:56 | ABEL BELATHEW |  | 002-207003 | DISCONNECT DROP CABLE | COMPLETED | DET 2
2021-12-15 | 7:00 | 2:48 | NARAN PINDORIA |  | 002-006991 | HFC SUPPORT | ESCALATED | DET 6
2021-12-15 | 7:00 | 4:10 | EYOSIAS DAMTEW |  | 002-039247 | HFC INTERNET INSTALL | COMPLETED | DET 2
2021-12-15 | 7:00 | 4:47 | NANCY NJUINJUI |  | 002-984164 | GPON SUPPORT | COMPLETED | DET 6
2021-12-15 | 7:00 | 6:15 | EMMA WACHIRA |  | 002-161734 | EQUIPMENT PICKUP | COMPLETED | DET 6
2021-12-15 | 7:00 | 6:30 | VIRGINIA RECZEK |  | 002-154222 | HFC SUPPORT | COMPLETED | DET 2
2021-12-15 | 7:00 | 7:37 | ANGIE WANJIKU |  | 002-035182 | GPON SUPPORT | COMPLETED | DET 6
1

## 15DECEMBER 2021
TARGET PER DAY | 7
NUMBER OF TEAMS | 2
TOTAL EXPECTED OUTPUT PER SLOT | 14
| 6.00-8.00 | 8.00-10.00 | 10.00-12.00 | 12.00-2.00 | 2.00-4.00 | 4.00-6.00 | 6.00-8.00 | 8:00-9:00 | TOTAL
DET 2 |  |  | 3 |  |  | 1 | 1 |  | 5 | 10
DET 6 |  |  |  |  | 1 | 1 | 2 |  | 4
TOTAL DONE
Customer Rescheduling/to call back
Customer Unreachable
G-TECH Technical (Routing)
Addtap
Client/ Management access issue/ wrongly addressed
WGK Technical (Signals/Approval)
Commercial (Coverage,MDU,NSR)
PreWired(No power)
Total Undoable Jobs per Slot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28– 7– 2020
[5 empty] | 4" | ?;LKJHGFDSDFGHJMK,L.;/'